## Program Tracker
Annexure C: Programme Tracker
DISTRICT | Deliverables | Overall Target | Cummulative Target till date (June to March 24) | Actuals till date (June to March 24) | % Achieved | Q1 |  |  |  |  | Q2 |  |  |  |  | Q3 |  |  |  |  | Q4
[6 empty] | June 2023- September 2023 |  |  |  |  | October 2023 - December 2023 |  |  |  |  | January 2024 - March 2024 |  |  |  |  | April 2024 - June 2024
[6 empty] | Target | Actuals (M) | Actuals (F) | Actuals (Total) | % Achieved | Target | Actuals (M) | Actuals (F) | Actuals (Total) | % Achieved | Target | Actuals (M) | Actuals (F) | Actuals (Total) | % Achieved | Target | Actuals (M) | Actuals (F) | Actuals (Total) | % Achieved
Kerala - Ernakulam | No of children screened | 30000 | 30000 | 30528 | 101.8% | 10000 | 4767 | 3482 | 8249 | 82.49% | 15000 | 7422 | 7155 | 14577 | 97.18% | 5000 | 3494 | 4208 | 7702 | 154% |  |  |  | 0 | #DIV/0!
| No. of Children prescribed Spectacles | 1800 | 1800 | 1907 | 105.9% | 600 | 283 | 211 | 494 | 82.33% | 900 | 497 | 546 | 1043 | 115.9% | 300 | 159 | 211 | 370 | 123.3%
| No of Children provided spectacles | 1800 | 1800 | 1907 | 105.9% | 600 | 0 | 0 | 0 | 0% | 900 | 455 | 388 | 843 | 93.67% | 300 | 484 | 580 | 1064 | 354.7%
| No of Children referred for surgery | 45 | 45 | 43 | 95.56% | 0 | 20 | 12 | 32 | #DIV/0! | 23 | 3 | 5 | 8 | 34.78% | 22 | 2 | 1 | 3 | 13.64%
| No of Children provided surgery | 20 | 20 | 2 | 10% | 0 | 0 | 0 | 0 | #DIV/0! | 10 | 0 | 0 | 0 | 0% | 10 | 1 | 1 | 2 | 20% |  |  |  | 0 | #DIV/0!
| No of Schools covered | 50 | 50 | 50 | 100% | 15 |  |  | 12 | 80% | 25 |  |  | 20 | 80% | 10 | 0 | 0 | 18 | 180% |  |  |  | 0 | #DIV/0!
| No of Teachers Trained | 50 | 50 | 50 | 100% | 15 | 2 | 30 | 32 | 213.3% | 25 |  | 18 | 18 | 72% | 10 | 0 | 0 | 0 | 0% |  |  |  | 0 | #DIV/0!
| Spectacle wearing compliance after 3 months | 60% | 900 | 484 | 53.78% | 0 | 0 | 0 | 0 | #DIV/0! | 360 | 0 | 0 | 0 | 0% | 540 | 261 | 223 | 484 | 89.63% | 180 |  |  | 0 | 0%
Spectacles wearing compliance was checked for 711 children out of which 453 wear using spectacles regularly, 31 were using occassionally, and 227 were not using
Note on O6: ====== ID#AAABS0l6wII Lenovo (2024-07-30 05:16:25) Lenovo: 3 referred chilldren visited hospital in Q2 and prescribes spectacles.
Note on O7: ====== ID#AAABS0l6wIY Lenovo (2024-07-30 05:16:25) 494 spectacles from Q1
Note on T6: ====== ID#AAABS0l6wH8 Lenovo (2024-07-30 05:16:25) 37 referred children from previous quarter visited hospital and prescribed spectacles
Note on T7: ====== ID#AAABS0l6wIU Lenovo (2024-07-30 05:16:25) 694 spectacles from Q2

## Children Screening Details
Children Screening Details
Record.No | Month | Name of the Child | Age | Gender | School Type | School Name | School Location | State | Remarks | Screening (Y/N) | Sepctacles Prescribed (Y/N) | Spectacles issued (Y/N) | Surgery Advised (Y/N) | Surgery Provided (Y/N)

## Surgery details
Surgery Details
Sr.no | Name of student | Age | Gender | School Name | School Location | State | Type of surgery | Date of surgery | Eye operated upon | Phase

## Teacher training
Teacher Training
SL NO | Name of school | School Location | State | Month of Training | Name of teacher | Gender | Trained (Y/N)

## Spectacles compliance
SL NO | NAME OF THE STUDENT | AGE | GENDER | SCHOOL NAME | STATE | SPECTACLE PROVIDED ON | FOLLOW-UP DONE ON | WEARING COMPLAINCE AFTER 3 MONTHS | REASON FOR NOT WEARING